## Sheet1
Sprint #1 Report
Actions to stop doing | Actions to start doing | Actions to keep doing | Work completed (or not) | Work Completion Rate
Stop having such short scrum meetings, we could use more time to make sure we understand our tasks and get up to speed with each other's current status. | Add a few more minutes to scrum meetings for further detail. | Keep meetings as consistent, attendance at meeting is great. | HTML Skeleton is finished for project, along with learning code to implement different languages and functions into the skeleton | 13 hours completed
|  | Communication as a team is really good. | Need to create and implement more functions to the skeleton | 3 user stories completed
Willingness to contribute and add new user stories